| Priority | Action | Existing Action? | City of Albany Role | Expected outcome(s) | Measure | Timeline | Resource implication | Stakeholders | Responsibility (department /role) | Information or material action | Alignment to State PHP objectives and priorities | Priority Risk Factor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Healthy Active Lifestyles |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Improve the provision and promotion of affordable, healthy food and drink choices at community facilities and events. | 1.1.1 Amend the Event Food Vendor application process to encourage vendors to provide healthy food/drink choices | Yes | Planning & Delivery | Food Vendors start to provide more healthy food options at events | Updated food vendor EOI | Q 2 2026/27 | Officer time | WACHS | Events Team | Information | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet |
|  | 1.1.2 Identify opportunities to provide free fruit at City of Albany events | No | Planning & delivery | Enhanced family friendly events Encourage healthy eating at community events Shift in community expectations | % of fruit remaining at end of day | Subject to funding | Officer time | Local suppliers Funding/sponsorship partner | Events Team | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet Equitable Access |
| 1.2 Support residents to develop skills and capacity to grow and prepare healthy foods. | 1.2.1 Promote and support opportunities for healthy food skills programs and initiatives for priority populations | Yes | Knowledge Building | Increase in knowledge on healthy cooking | # of participants Demographic of participants | Subject to securing funding | Officer time Existing budget allocation Grant opportunities | Pivot AYSA Anglicare Shalom House WACHS WACHS - GSAH | Community Development Library Recreation Services | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet |
|  | 1.2.2 Continue to provide a seed exchange library at the Albany Public Library, to encourage people to grow their own food. | Yes | Planning & Delivery | Increased knowledge on gardening, horticulture and sustainable food systems Reduce household food costs | # of varieties available # of seed packets distributed | Ongoing | officer time | RCNC Community Garden | Library | Material Action | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Diet Equitable Access |
|  | 1.2.3 Promote Community Sustainability Grants for projects that encourage and support skills and capacity to grow foods. | Yes | Planning & Delivery | Increase in projects that support skills and capacity to grow foods | # of grants distributed # of activities funded | Ongoing | Officer time Budget Allocation | Community groups | Sustainability Comms | Material Action | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Diet Equitable Access |
|  | 1.2.5 Identify opportunities to promote education resources on healthy eating (Live Lighter, Cancer council etc) at City Venues | No | Knowledge Building | Increase in knowledge on healthy cooking | # of educational resources used | Ongoing | Officer time Grant funding | Cancer Council Live Lighter WACHS | Recreation Services Library Com Dev | Material Action | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Diet |
| 1.3 Advocate for and support community access to affordable, healthy produce and food outlets | 1.3.1 Advocate for and support State and Federal initiatives that promote healthy food environments and responsible alcohol consumption, including appropriate regulation of fast food and alcohol outlets. | Yes | Leadership & policy | Vulnerable community members have access to affordable healthy produce. Increase in the number of affordable food outlets | # of services in the community | Ongoing | Officer time | WA State Govt Federal Govt | Environmental Health / Community Development | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet Alcohol consumption Environmental Safety & Quality |
| 1.4 Improve accessibility, amenity and promotion of pathways to increase the use of active and public transport | 1.4.1 Strengthen and implement an integrated urban greening framework to increase tree canopy and enhance amenity, shade and walkability across the City, including through policy, planning, programs and community initiatives. | Yes | Planning & Delivery | Increased urban tree canopy and improved shade, amenity and comfort of streets and public spaces, supporting walkability, active transport and climate resilience. | Implementation of updated urban tree strategy / policy framework Number of streets or areas improved through greening initiatives Street tree asset valuation | Ongoing | Budget allocation Officer Time |  | Reserves Sustainability Team (or lead / co-lead?) Development Services (Planning & Development Engineering) Assets Community Development | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Environmental Safety & Quality Physical inactivity |
|  | 1.4.2 Identify and deliver opportunities to improve the safety, connectivity and amenity of active and public transport infrastructure, supported by integrated land use planning to enhance accessibility to key community places and spaces. | Yes | Planning & Delivery | Increase in community members using active transport Increase in number of people using public transport | Metres of path installed & maintained # of bus shelters Community perception | Ongoing | Budget allocation Officer Time Grant opportunities | CoA Teams State agencies (Public Transport Authority, Main Roads, Department of Health) | Assets / Com Dev Development Services (Planning & Development Engineering) | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity Environmental Safety & Quality |
|  | 1.4.3 Apply Healthy Active-by-Design principles to CoA major infrastructure projects | Yes | Planning & Delivery | Infrastructure projects are designed to support active transport | # of projects utilising Healthy by Active Design | Ongoing | Budget allocation Officer Time Grant opportunities | Heart Foundation | Major Projects Engineering | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity Environmental Safety & Quality |
|  | 1.4.4 Utilise City communications channels to promote the City's path works program encompassing capital works and grant funded projects. | Yes | Knowledge building | Positive sentiment and community understanding about the associated works. | # of social media posts | Ongoing | Budget allocation Officer Time Grant opportunities | Local media outlets | Comms | Information | Promote | Physical inactivity Environmental Safety & Quality |
|  | 1.4.5 Investigate opportunities for journey planning tools and cycle map options to encourage more cycling and active lifestyles | No | Planning & delivery | Community members can plan commuting or recreational trips by bike | Journey planning tool developed | Completion in 2027 | Officer time Budget allocation (if not possible to develop in house) | Department of Transport | Sustainability Assets | Information | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.4.6 Support, promote and advocate for schools to increase riding by students with the Your Move Schools program, and access to bike education, training and delivery | Yes | Knowledge building | Increase in active transport to school | Number of schools involved in Your Move Schools program | Ongoing | Officer time | Department of Transport Schools | Sustainability | Material | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
| 1.5 Maximise safe, active and passive outdoor recreation opportunities through the development and promotion of City parks, reserves, playgrounds, and open spaces | 1.5.1 Utilise City communications channels to promote the City’s reserves, open spaces, sporting fields, parks and playgrounds. | Yes | Planning & delivery | Positive sentiment and community understanding about the City’s open spaces, sporting fields, parks and playgrounds. | # of social media posts and engagement activities. | Ongoing | Budget allocation Officer Time |  | Comms Reserves Recreation Services | Information | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.5.2 Precinct park planning to ensure a variety of experiences and spaces | No | Planning & delivery | Albany has a variety of park | Number of parks improved | Ongoing | Budget allocation Officer Time Grant opportunities | Kidsafe Park users | Reserves | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.5.3 Ensure the provision and equitable distribution of accessible public open space in new growth areas through strategic planning, structure planning and subdivision processes | No | Planning & delivery | Improved access to well-located and functional public open space that supports physical activity, social interaction and community wellbeing. | % of new dwellings in growth areas within walkable distance of Public Open Space (POS) POS provision aligned with State policy requirements Inclusion of minimum POS provision requirements in structure plans/subdivision approvals | Ongoing | Officer time | CoA teams Developers / landowners WAPC / DPLH (subdivision + policy context) | Planning Reserves Assets Community Development Recreation Services Development Engineering | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity Equitable access |
|  | 1.5.4 Review availability of drink fountains and investigate opportunities to expand the number of fountains | No | Planning & delivery | More water fountains are available in parks | Number of fountains installed | Subject to funding | Budget allocation Officer Time Grant opportunities |  | Reserves Sustainability Assets - support only | Material action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet |
| 1.6 Provide, manage and promote a range of inclusive and affordable recreational, sporting, health and fitness facilities and programs. | 1.6.1 Development of the Sport & Recreation Strategy to ensure strategically targeted and prioritised sports and recreation planning to serve changing community needs. | Yes | Planning & delivery | Completion of Sport & Recreation Strategy | Adoption of the strategy by Council | Jul-26 | Budget allocation Officer time |  | Recreation Services | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.6.2 Continue to locally administer and promote state and federal physical activity/sports initiatives (i.e. KidSport, Regional Pools Program) | Yes | Partnerships | Removal of financial barriers to children participating in sports and accessing pool | Number of participants in programs | Ongoing | Officer time State Govt support for program | CITS | Recreation Services | Material Action | Prevent Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity Equitable access |
|  | 1.6.3 Delivery of joint ALAC library programming e.g. Splish Splash and Story Ride | Yes | Planning & delivery | Families with young children are introduced to the range of recreational facilities provided by the City. | # of participants | Ongoing | Officer time |  | Recreation Services Library | Material Action | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.6.4 Continue to provide a Bike desk at the Albany Public Library | Yes | Planning & delivery | Library uses have the opportunity to be active while studying/using the Library | Number of times used | Ongoing | Maintenance budget |  | Library | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.6.5 Continue to provide LLY & GoYouth membership programs | Yes | Planning & delivery | Seniors and young people have access to affordable gym membership programs | Number of members in each program Improvement in fitness/wellbeing for attendees | Ongoing | Officer time/FTE |  | Recreation Services | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical activity Equitable access |
|  | 1.6.6 Work with City facilities such as ALAC, Library, Arts & Culture and events to promote a varied range of community programs through the City's communications channels. | Yes | Planning & delivery | A range of inclusive and affordable programs are promoted | # of social media posts # of media metions | Ongoing | Officer time Budget allocation |  | Comms Community Services | Information | Promote Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
|  | 1.6.7 Ensure provision of suitably located land for sport and recreation facilities through structure planning and subdivision processes, aligned with identified community needs. | Yes | Planning & delivery | Identification and provision of appropriately located land in new development areas to support the delivery of sport and recreation facilities that meet current and future community needs. | Provision of land for sport and recreation facilities identified through structure planning and subdivision approvals. | Ongoing | Officer time | Developers / landowners WAPC / DPLH CoA teams | Planning Recreation Services Reserves Assets | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity Equity & Access |
|  | 1.6.8 Explore opportunities to add health and wellbeing components to existing programs supporting Aboriginal residents | No | Planning & delivery | Improved health outcomes for Aboriginal community members | # of programs valued added to | Subject to external funding | Officer time | WACHS GS AH ACCOs | Com Dev Recreation Services | Material Action | Promote Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet Physical inactivity Mental health |
|  | 1.6.9 Identify opportunities to embed dental health education into activities and events | Yes | Planning & delivery Partnerships | Community members have improved access to dental health information. | # of opportunities identified | Subject to external funding | Officer time | WACHS | Community Services | Material Action | Promote Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Equitable access Diet |
| 1.7 Create and promote a health-promoting workplace for City staff and council. | 1.7.1 Develop and facilitate an annual staff health and wellbeing program of activities, promotions, and events | Yes | Planning & delivery | Annual calendar of events is delivered | Staff participation staff feedback | Ongoing | Officer time Budget allocation | Various health organisations LGIS | People & Culture | Material Action & Information | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Diet Physical inactivity Mental Health Injury Smoking Alcohol consumption |
|  | 1.7.2 Promote and consider incentives to encourage active transport to work | No | Planning & delivery | More active staff | # of staff using active transport each year | Ongoing | Officer time Budget allocation |  | People & Culture | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Physical inactivity |
| 1.8 Promote strategies for maintaining good mental health, and improve awareness of local mental health services | 1.8.1 Use Act Belong Commit messaging in City promotions to encourage people to engage in community for good mental health | No | Knowledge building | ncrease in mental health literacy | # of events/activities with ABC messaging | Ongoing | Officer time | Curtin University | Comms Library Arts & Culture Recreation Services | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental Health |
|  | 1.8.2 Assist in the promotion and distribution of ACE cards & ACE messaging | No | Partnerships | Increase in suicide prevention literacy | # of events cards distributed # of venues ACE video displayed | Ongoing | Officer time | GSSPAG | Com Dev | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental Health |
|  | 1.8.3 Promote special awareness days, trainings and workshops that can help in community support for those experiencing mental health challenges | No | Partnerships | Increase in mental health literacy | # of trainings/events promoted | Ongoing | Officer time | Palmerston RU OK Day MHC Black Dog Institute Stand By Thirrili | Com Dev Comms | Information | Prevent Aboriginal Health& Wellbeing Equity & Inclusion | Mental Health |
| 1.9 Advocate for increased services to support the community’s health and wellbeing as supported through data trends (dental, hydrotherapy pool) | 1.9.1 Advocate for the hydrotherapy pool to be reopened at the Albany hospital. | No | Leadership & Policy | Community members have access to affordable warm water therapy, which can assist with managing chronic conditions | The hydrotherapy pool is reopened | Ongoing | Officer time | WACHS | Mayor/Office of CEO Com Dev | Material Action | Prevent Aboriginal Health& Wellbeing Equity & Inclusion | Equitable access |
|  | 1.9.2 Advocate for expansion of subsidised dental care for low income earners | No | Leadership & policy | Low income earners have access to affordable dental care without long waiting periods. | Wait list times reduced. Hospitalisations for dental conditions reduced | Ongoing | Officer time | WACHS | Mayor/Office of CEO Com Dev | Material Action | Prevent Aboriginal Health& Wellbeing Equity & Inclusion | Equitable access |
| Socially Connected, Inclusive & Empowered |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority | Action | Existing Action? (yes/no) | City of Albany Role | Expected outcome(s) | Measure | Timeline | Resource implication | Stakeholders | Responsibility (department/role) | Information or material action* | Alignment to State PHP objectives and priorities | Priority Risk Factor |
| 2.1 Improve the recognition and engagement of the local Aboriginal community, culture and history | 2.1.1 Promote and facilitate events and initiatives to align with Reconciliation Week and NAIDOC each year | Yes | Planning & delivery Knowledge building Leadership & Policy Partnerships | Strengthen relationships between Indigenous and non-indigenous communities Promote local Menang culture Increased willingness to have respectful conversations about culture and history | No of events facilitated No of events promoted No of attendees at each event/initiative Feedback from Elders | Reconciliation Week - May/June NAIDOC Week - July GS Noongar Festival - October | Officer time Budget allocation | ACCO's WACHS - GSAH GS Museum AEC | Com Dev Arts & Culture Library Communications | Material Action | Promote Aboriginal Health& Wellbeing | Mental Health |
|  | 2.1.2 Continue to install signage and provide interpretive information for areas identified by Indigenous reference group sites across Albany | Yes | Planning & delivery Knowledge building | Increased awareness and use of Menang language | No of dual named signs installed No of interpretive signs installed Completion of ArcGIS Storymap | Ongoing | Officer time Budget allocation | Wagyl Kaip | Reserves Com Dev Major Projects | Material Action | Promote Aboriginal Health& Wellbeing | Mental health |
|  | 2.1.3 Provide funding opportunities for local indigenous led initiatives through the Indigenous Projects Funding program | Yes | Planning & delivery | Increased visibility of Aboriginal culture Increased participation of Aboriginal community members in events More opportunities for Aboriginal led initiatives | No of applications No of projects funded | Annual grant program | Officer time Budget allocation | ACCO's | Com Dev | Material Action | Promote Aboriginal Health& Wellbeing | Mental Health |
|  | 2.1.4 Work with City teams to promote recognition of the local Indigenous community. | Yes | Planning & delivery Knowledge building | Increased recognition of the local indigenous Menang culture | No of initiatives promoted | Ongoing | Officer time Budget allocation | Elders | Comms | Information | Promote Aboriginal Health& Wellbeing | Mental Health |
| 2.2 Provide and support community events, services, facilities and programs that develop people's compassion, sense of belonging and purpose | 2.2.1 Continue to develop the City’s arts, cultural and community development services, facilities, programs, and events, with a focus on engaging priority populations | Yes | Planning & delivery | A diverse range of programs is delivered, which focus on priority populations | No of events facilitated No of events promoted No of attendees at each event/initiative Feedback from participants | Annual programming | Officer time Budget allocation | ACCO'S Albany Regional Prison | Com Dev Arts & Culture Library Comms | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health |
|  | 2.2.2 Support and promote local social services for vulnerable and/or culturally and linguistically diverse people in the community | Yes | Planning & Delivery Knowledge building | Vulnerable community members are aware of and have access to local support services | Information on local services is available | Ongoing Annual programming (Harmony week) | Officer time Budget allocation | Art after Dark - Gorenang Moortabiin Denmark Arts ALOTCO SEA AEC Pride | Arts & Culture Com Dev Events Comms | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health Equitable access |
|  | 2.2.3 Continue to support community groups to hold events and deliver programs through the provision of grant funding. | Yes | Planning & delivery | Community groups are supported to deliver a range of programs and events | No of enquiries No of applications No of projects/events funded | Annual funding rounds | Budget allocation Officer time | Community Groups | Arts & Culture Com Dev Events | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health Equitable access |
|  | 2.2.4 Deliver and support initiatives that encourage the community to support people facing aging, serious illness, death or bereavement | Yes | Planning & delivery Knowledge building | Increase in death literacy | # of events # of participants | Palliative Care Week (May) Dying to Know Day (August) | Budget allocation Officer time | WAPHA Albany Hospice Aged care providers Palliative Care WA | Com Dev Arts & Culture Library | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health |
|  | 2.2.5 Identify funding opportunities to support the development of a 'Strike' style drop in program at the Albany Noongar Centre | No | Partnership | A drop-in style program is developed to provide a safe, supervised space for young people to connect. | Funding obtained for the pilot program | Subject to funding | Funding Officer time | Albany Aboriginal Corporation Kadadjiny Aboriginal Corporation Wagyl Kaip Elders Palmerston Rio Tinto NIAA | Com Dev | Material Action | Prevent Aboriginal Health& Wellbeing | Mental health Physical inactivity Diet Equitable Access Injury |
| 2.3 Develop and support initiatives that reduce social isolation and loneliness | 2.3.1 Continue to encourage community members to get to know their neighbours through initiatives such as Neighbour Day | Yes | Planning & delivery | Increase in neighbourly behaviour Increase in people knowing their neighbours | # of Neighbour Day events funded | March each year | Budget allocation Officer time | Relationships Australia | Com Dev | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health |
|  | 2.3.2 Continue to deliver activities through the Library & VAC e.g Loop by Loop, Book Chat, Make it Monthly, Art Room | Yes | Planning & delivery | Community members have access to a range of affordable recreational activities to connect with likeminded individuals. | # of participants # of programs delivered | Ongoing | Budget allocation Officer time |  | Library Arts & Culture | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Mental health |
| 2.4 Support families to embed early literacy practices with children | 2.4.1 Continue to deliver Better Beginnings early literacy packs to families with supporting library programming | Yes | Partnership Planning & delivery | Increase in early literacy | Number of packs delivered | Ongoing | Officer time | SLWA, Child Health nurses | Library | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Equitable Access |
| 2.5 Improve community access to information about community groups, facilities, events and resources | 2.5.1 Continue to improve the CoA website navigation, content, and accessibility | Yes | Planning & delivery | Community members find the website easy to navigate, and they can easily locate the information they require. | Feedback from staff and community | Ongoing | Officer time | Marketforce | Comms IT | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | All |
|  | 2.5.2 Continue to promote the My Community Directory and support community groups to register | Yes | Planning & delivery | MCD is a comprehensive list of local community groups and services | # of groups registered | Ongoing | Officer time Budget allocation (Annual membership fee) | Community Information Services | Com Dev | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | All |
|  | 2.5.3 Library continues to be a communication point through the provision of Notice boards, posters, flyers, newsletters, etc. | Yes | Planning & delivery | The library continues to be a central information point for the community on upcoming events and activities. | # of people accessing newsletter # of people accessing the library | Ongoing | Officer time |  | Library Comms | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | All |
|  | 2.5.4 Work with My Community Directory to house an up to date list of community groups in Albany. | Yes | Planning & delivery Partnerships | MCD is a comprehensive list of local community groups and services | # of groups listed on site | Ongoing | Officer time Budget allocation (Annual membership fee) | Community Information Services | Com Dev | Information | Promote Aboriginal Health& Wellbeing Equity & Inclusion | All |
|  | 2.5.5 Encourage shared use of under-utilised spaces to reduce need for new built infrastructure | Yes | Planning & delivery Knowledge building | Community facilities have multiple user groups, which leads to more sustainable community groups | # of groups requesting accommodation that are found a co-located location. | Ongoing | Officer time | CITS | Com Dev Leasing Rec Services | Material Action | Promote Aboriginal Health& Wellbeing Equity & Inclusion | Equitable Access |
| 2.6 Support volunteer recognition, attraction & retention for community groups | 2.6.1 Develop, support, and promote initiatives that provide opportunities for community volunteerism | Yes | Planning & delivery Knowledge building Partnerships | Albany has a strong volunteer culture and strong community groups. | No of City of Albany volunteers Number of bush care events % of community volunteering (census) | Ongoing | Officer time | ARVS | Com Dev Reserves NAC Library Visitors Centre Sustainability People & Culture | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health |
|  | 2.6.2 Explore corporate volunteering opportunities for staff and elected members | No | Planning & delivery Leadership & policy | Staff and elected members can support community groups through corporate volunteering. | Opportunities tabled with EMT for consideration | Ongoing | Officer time | ARVS | Com Dev People & Culture | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health |
|  | 2.6.3 Explore volunteer recognition incentives for volunteers and employers to encourage volunteering | No | Planning & delivery Leadership & policy | Volunteers are supported by their employers to continue to respond to emergency callouts. | Development program | 2027/28 | Officer time Local sponsorship | ARVS | Emergency Services Com Dev | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health |
|  | 2.6.4 Maintain a service agreement with ARVS to support volunteer development and engagement. | Yes | Planning & delivery | ARVS continue to deliver services to the City and volunteer-run organisations | As per service agreement | Three year agreement, review subject to performance | Budget allocation | ARVS | Com Dev | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health |
|  | 2.6.5 Continue to provide training and grants that can assist with the training and support of volunteers | Yes | Planning & delivery | Increase in the sustainability of community groups Increase in trained volunteers | # of volunteers trained # of groups funded | Ongoing | Budget allocation Officer time | Community groups | Com Dev | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health Equitable access |
|  | 2.6.6 Support activities and events that recognise volunteer contribution | Yes | Planning & delivery Leadership & policy | Volunteers feel valued and recognised | # of activations # of volunteers involved | May – Volunteer Week Dec – Thank a volunteer Day | Budget allocation Officer time | ARVS | Com Dev Albany Heritage Park Reserves People & Culture | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health Equitable access |
| 2.7 Support and advocate for initiatives aimed at improving access to affordable housing and transport | 2.7.1 Contribute to public policy reviews and discussions on affordable housing and transport access | Yes | Leadership & policy | Informed and coordinated City input into State and Federal policy discussions to support improved access to affordable housing and transport. | Number of policy submissions or contributions made to State and Federal initiatives. | Ongoing | Officer time | Dept Transport Dept Housing Shelter WA | Office of CEO Mayor Planning Com Dev | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Equitable access Mental Health Injury Environmental safety & Quality |
|  | 2.7.2 Complete delivery of essential infrastructure at McAlpine Rise | Yes | Planning & delivery | An increase in affordable housing options. | Completion of the development and sale of blocks | 31 March, 2027 | Officer time Grant allocation | Dept of Infrastructure, Transport, Regional Development, Communications, Sport & the Arts | Engineering Major Projects | Material Action | Prevent Aboriginal Health & Wellbeing Equity & Inclusion | Equitable access Mental Health Injury Environmental safety & Quality |
| Safe, Prepared & Protected |  |  |  |  |  |  |  |  |  |  |  |  |
| Priority | Action | Existing Action? (yes/no) | City of Albany Role | Expected outcome(s) | Measure | Timeline | Resource implication | Stakeholders | Responsibility (department/ role) | Information or material action* | Alignment to State PHP objectives and priorities | Priority Risk Factor |
| 3.1 To perform the functions and apply the objects and principles confirmed in the Public Health Act 2016 (the Health Act). | 3.1.1 To initiate, support and manage public health planning in the City of Albany. | Yes | Planning & delivery | Develop coordinate and manage PH Planning applying a responsive and evidence based approach to public health outcomes. | The Health and Wellbeing Plan developed and published with the timeframes required in the Health Act. | Reviewed annually and redeveloped within the 5 year period required in the Health Act. | Officer time | Dept Health, Council and Exec, Community, and key local and regional agencies. | EH Com Dev | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
|  | 3.1.2 Develop and implement locally relevant programs and policies that support public health planning and health and wellbeing. | Yes | Planning & delivery | A range of programs aare delivered to support public health and wellbeing. | The programs s are relevant to local population health profiles. | Ongoing | Officer time Budget allocation Grant Funding | Dept Health, Council and Exec, Community, and key local and regional agencies. | EH Com Dev | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
|  | 3.1.3 To perform the functions to administer and enforce the objects and principles of Health Act. | Yes | Planning & delivery | Provide environmental health services and facilities to perform and support the functions and administer the Health Act. | Meeting statutory obligations, managing risks effectively, and supporting community wellbeing outcomes | Ongoing | Officer time |  | EH | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
| 3.2 To prepare, implement and report on plan aligned with the State Public Health Act 2016. | 3.2.1 Develop the plan and objectives that are consistent with the State Public Health Plan. | Yes | Planning & delivery | Relate objectives and actions to the State Public Health Plan objectives and priorities. | Undertake annual reviews and report to Dept of Health | Ongoing | Officer time | Exec and Council | EH Com Dev | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
|  | 3.2.2 Interrelate the Health and Wellbeing Strategy as an informing plan for the planning framework required under LG Act. | Yes | Planning & delivery | Consider the Health and Wellbeing Strategy as part of reviews and preparations of existing and future organisational strategic planning. | How the Health Wellbeing Plan relates to the integrated planning and reporting framework. | Ongoing | Officer time | Exec and Council | EH Com Dev | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
|  | 3.2.3 Prepare and implement a compliant Plan that identifies the City of Albany current and emerging public health needs. | Yes | Planning & delivery | A compliant and endorsed Plan that is evidence-based, has relevant adaptive actions, and can be measured and reported | The Health & Wellbeing Plan is endorsed by Council and includes adequate stakeholder engagement and an assessment of population data to relate objectives to annual reviews and reporting. | Ongoing | Officer time | Exec and Council | EH Comm Dev | Information & material actions | Promote, protect, prevent, enable, Aboriginal health & wellbeing Equity & inclusion. | All |
|  | 3.2.4 Prepare an annual Public Health Report as per the requirements of the Public Health Act. | Yes | Planning & delivery | City is compliant with reporting requirements | Report submitted | Each year | Officer time | Dept Health | EH Com Dev | Information & material actions | Enable | All |
| 3.3 Enforce and promote local government statutory requirements of relevant State public and environmental health legislation | 3.3.1 Undertake health risk and impact assessments to ensure public buildings and events are safe | Yes | Planning & delivery | The public is kept safe whilst attending public buildings and events. | Percentage of assessed versus total events/public buildings | Ongoing | Officer time |  | EH Events Approvals | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.2 Provide advice and support to the community about key public health risks | Yes | Planning & delivery Knowledge Building | Community is kept informed of current risks and associated impacts | Number of customer requests actioned Number of media releases | Ongoing | Officer Time |  | EHO Comms | Information | Prevent Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.3 Undertaken public health monitoring program to manage risks of food business related non-scheme potable water. | Yes | Planning & delivery | The City monitors food businesses with non-scheme potable water supply | No of water testings undertaken | Ongoing | Officer time |  | EH | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.4 Monitor and enforce public aquatic facilities water quality in accordance with public health legislation. | Yes | Planning & delivery | Monitoring of all public aquatic facilities water quality. | No of water testings undertaken | Ongoing | Officer time |  | EH | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.5 Undertake health impact assessment of building and planning applications | Yes | Planning & delivery | Provision of health advice to development services for applications | No of health impact assessments for building and planning undertaken | Ongoing | Officer time |  | EH | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.6 Undertaken Food Premises Surveillance in accordance with Food Act 2008 and Food Standards Code | Yes | Planning & delivery | Increased levels of compliance with food safety regulations and subsequent community protection | No of surveillances undertaken | Ongoing | Officer time |  | EH | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.7 Continue the Food Surveillance Sampling Program with local residents, business operators, and primary producers | Yes | Planning & delivery | Increased levels of compliance with food safety regulations and subsequent community protection | No of samples undertaken | Ongoing | Officer time |  | EH | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.8 Provide food handler and hygiene training to community groups as required including online access to Department of Health endorsed programs. | No | Planning & delivery | Availability and free access to food handler training. | Number of in-house training events Full compliance with the Food Standards requirements for food handler skills and knowledge. | Ongoing | Officer time |  | EH | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.9 Continue to promote responsible waste disposal and minimisation, use of bulk collections, e-waste drop off, etc. | Yes | Planning & delivery | Increase in use of recycling programs (eWaste etc), Reduction in the amount of waste going to landfill | Tons of waste diverted from landfill Tons of waste collected through bulk collections (ie eWaste) | Ongoing | Officer time Budget allocation |  | Sustainability Comms | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.3.10 Promote Household Hazardous Waste disposal program, including in rural areas | Yes | Planning & delivery | Increased understanding of what hazardous waste is, and how to dispose of it safely | Weight of house hazardous weight collected (Rural and Urban) | Ongoing | Officer time Budget allocation |  | Sustainability Comms | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
| 3.4 Minimise community exposure to environmental tobacco smoke | 3.4.1 Continue to implement a Smoke-free Outdoors Policy and community awareness campaign for the sports and recreation precinct, public building entrances, and events. | Yes | Planning & delivery | Community are not exposed to second hand smoke at City venues, events and public buildings. | Number of new or updated Smoke-free signs at Centennial Park and other venues? | Ongoing | Officer time |  | Events EH Facility Managers | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury Smoking |
| 3.5 Monitor and support infectious disease management | 3.5.1 Apply a risk based approach to the CoA Mosquito Management Program Plan and Contiguous Local Authorities Group. | Yes | Planning & delivery | Respond to community concerns and state department reports. | Appropriate control strategies applied to program triggers | Ongoing | Officer time Budget allocation |  | EH | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & Quality Injury |
|  | 3.5.2 Provide prompt support for the investigation of notifications of outbreaks. | Yes | Planning and delivery | Respond to community concerns and state department reports. | Number of investigations completed | As required | officer time | Dept Health | EH | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & Quality Injury |
|  | 3.5.3 Continue to map reports of syringes found in the community and provide sharps containers in key locations to ensure safe disposal. | Yes | Planning and delivery | Sharps disposal containers are located in places that support safe disposal. | # of sharps bins # of reports of syringe littering Maintenance of the syringe littering map | Ongoing | Officer time | WACHS | Com Dev Depot | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Environmental safety & Quality Injury |
| 3.6 Support environmental health resourcing and professional development | 3.6.1 Support the Department of Health and Environmental Health Australia initiatives promoting environmental health mentorship and training. | Yes | Leadership & Policy | Increase the capacity of Environmental Health Team | Hours of professional development | Ongoing | Officer time Budget allocation | Dept Health EH Australia | EH | Material Action | Enable | Environmental safety & Quality |
|  | 3.6.2 Promote the environmental health profession as a career choice | Yes | Leadership & policy | Environmental health is seen as a desirable career. | Attendance at career expos | As opportunity arises | Officer time |  | EH People & Culture | Material Action | Enable | Environmental safety & Quality |
| 3.7 Support and raise community awareness of crime and injury prevention initiatives and resources | 3.7.1 Contribute to public policy reviews and discussions on alcohol, drugs and family violence | Yes | Leadership & policy | The City is kept informed of current trends, and actively contributes to policy reviews and discussions | Attendance at LGSAODMG meetings | Ongoing | Officer time | LGSAODMG Palmerston WACHS Anglicare WAPOL Holyoak | Com Dev EH | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Alcohol consumption |
|  | 3.7.2 Work with relevant teams to actively promote relevant initiatives and resources at timely points across the year. | Yes | Planning & delivery | Community is informed and understanding of crime and injury initiatives and resources. | # of social media posts # of initiatives supported | Ongoing | Officer time |  | Comms | Information | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Alcohol consumption |
|  | 3.7.3 Continue to provide falls prevention kits and strength classes and promote to Seniors | Yes | Planning & delivery Knowledge building | Seniors have access to affordable programs and kits to reduce the instances of falls. | # of classes # of kits loaned out | Ongoing | Officer time | Injury Matters | Albany Public Library Recreation Services | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.7.4 Provide regular safety in the home workshops for community | No | Planning & delivery Knowledge building | Community have access to information and resources to improve safety in the home. | # of workshops held | Ongoing | Officer time | WAPOL WACHS Injury Matters DMIRS | Library Com Dev | Information | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.7.5 Continue to provide free graffiti removal kits to support rapid removal of graffiti | Yes | Planning & delivery | Less visible graffiti Increase in perception of safety | # of graffiti kits provided # of incidents of graffiti reported to Police | Ongoing | Officer time Budget allocation Grant opportunities | WAPOL | Com Dev Trades Library | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality |
|  | 3.7.6 Promote assisted residential bin service to support independence and falls prevention for approved applicants. | No | Planning & delivery | Increased applications for service. | # assisted service recipients | Ongoing | Officer Time | Veolia | Comms Waste Comm Dev | Information & material action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety & quality |
|  | 3.7.7 Promote reporting options for illegal dumping and other environmental damage, through Crimestoppers or City of Albany Report It | Yes | Planning & delivery Knowledge building | Reduction in illegal dumping | # of reports | Ongoing | Officer time | Veolia | Comms Rangers Reserves Ops Sustainability Compliance Emergency Services | Material Action & information | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality |
|  | 3.7.8 Continue to promote and support Adopt-a-Spot and other programs to address litter | Yes | Planning & delivery | Reduction in visible litter | # of adopt a spot groups | Ongoing | Officer time | Keep Australia Beautiful Keep Albany Beautiful | Comms Sustainability | Material Action & Information | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality |
|  | 3.7.9 Continue to track syringe litter to map hotspots, and prioritise sharp bin locations | Yes | Planning & delivery | Sharps containers are located in the most appropriate locations. | # of syringe litter | Ongoing | Officer time | WACHS | Com Dev | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental safety & quality Injury |
|  | 3.7.10 Embed health education into City programs that can address accidental poisonings | No | Planning & delivery | Community are informed on how to reduce the instances of accidental poisionings | # of programs # of participants | Ongoing | Officer time Grant opportunities | WACHS Injury Matters Pharmacies | Com Dev Recreation Services Library | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury |
|  | 3.7.11 Improve safety in Centennial park precinct by installing lighting in car parks and along footpaths | No | Planning & delivery | Improved lighting providing a safer sporting precinct. | Lighting is installed in car park Lighting of paths is completed | Subject to funding | Grant funding Officer time | Sporting Clubs | Recreation Services | Material Action | Protect Equity & inclusion Aboriginal Health & Wellbeing | Injury |
| 3.8 Digital literacy programs that address cybersafety and scam awareness | 3.8.1 Continue to develop and deliver digital awareness sessions around online safety and scam awareness | Yes | Planning & delivery Knowledge building | Residents have greater awareness on how to protect themselves online, and from scams | # of programs # of participants | Ongoing | Officer time | Office of Digital Inclusion | Library | Material action & information | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Mental health Equitable access |
| 3.9 Use design principles to enhance community safety in town planning and facility development | 3.9.1 Support the design and delivery of safe, legible and well-connected built environments through planning framework and processes, including local planning strategy, structure planning, consideration of subdivision referrals, implementation of local planning policy and the consideration of relevant development proposals. | Yes | Planning & delivery Leadership and Policy | Improved community safety and perception of safety through well-designed, connected and activated public spaces and where it interfaces with private spaces. | Consideration of safety and built design principles in strategic planning and relevant development application proposals. Incorporation of safety and design principles in approved structure plans and development proposals. | Ongoing | Officer time | Developers | Lead: Planning Support: Major Projects Reserves Assets Development Engineering Community Development | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Equitable access Mental health |
|  | 3.9.2 Apply CPTED to City of Albany infrastructure upgrades and developments | No | Planning & delivery | City infrastructure and developments are designed to minimise crime. | Consideration of CPTED is embedded in the design scope | Ongoing | Officer time Grant funding Budget allocation | Contractors | Major Projects Reserves Engineering & Assets | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury |
| 3.10 Ensure the City and the community is well prepared to respond effectively to and recover from major emergencies, disasters, or serious public health incidents. | 3.10.1 Undertake community education activities to raise awareness of emergency risks and preparedness. | Yes | Planning & delivery Knowledge building | Community is well informed and prepared for emergencies | # of education sessions held | Ongoing | Officer time Grant funding Budget allocation | DFES | Emergency Services Reserves EH | Information | Protect Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.10.2 Develop and train staff in emergency management, response, and recovery to support incidents. | No | Planning & delivery Knowledge building Leadership & Policy | The City has a well trained team to respond and recovery from emergencies. | #of staff trained | Ongoing | Budget allocation Officer time | DFES Red Cross | Emergency Services Com Dev People & Culture | Material action & information | Protect Aboriginal health & wellbeing Equity & inclusion | Enable |
|  | 3.10.3 Install of electronic fire danger rating boards across the LGA | No | Planning & delivery | Community and visitors are kept informed of the fire danger risk each day. | # of signs installed | Subject to funding | Grant Funding | DFES | Emergency Services | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety and quality |
|  | 3.10.4 Work with Aged care residential care to review and strengthen their planning and response. | No | Planning & delivery Knowledge building | Residential aged care providers have strengthened emergency response plans | Completed revised plans | 2026/27 | Officer time | DFES WAPHA Aged Care Providers St Johns | Emergency Services Com Dev | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety and quality |
|  | 3.10.5 Develop a response plan for brigade areas. | Yes | Planning & delivery | Each brigade has a detailed response plan. | # of plans completed | By 2029 | Officer time | DFES | Emergency Services | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety and quality |
|  | 3.10.6 Provide and promote access to counselling services to CoA emergency volunteers exposed to traumatic events | Yes | Planning & delivery | Volunteers are supported following a traumatic event. | # of volunteers supported | As required | Budget allocation | Contracted services | People & Culture Emergency Services | Material action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury Mental Health Environmental safety and quality |
|  | 3.10.7 Develop a plan to build the capacity of Health Services team to undertake hygiene and safety assessments in response to local and inter-regional public health outbreak and emergencies | No | Planning & delivery Knowledge building Leadership & Policy | Health services team are trained to respond to local and inter-regional public health outbreaks and emergencies | # of staff trained | Ongoing | Budget allocation Officer time |  | EH | Material Action | Enable | Environmental safety & quality |
|  | 3.10.8 Map existing assets that could be activated during an emergency (ie wheelchair buses, mobile hoists etc) | No | Planning & delivery Knowledge building Leadership & Policy | Detailed asset list developed that can be activated in an emergency | Completed asset mapping | 2026/27 | Officer time | NDIS agencies Aged care providers Taxi companies Medical practices | Com Dev | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.10.9 Use Person Centered Emergency Planning Tool to encourage vulnerable community members to prepare for emergencies | No | Planning & delivery Knowledge building | Vulnerable community members are better prepared for an emergency | # of PCEP completed # of PCEP facilitators trained | Ongoing | Officer time | DFES NDIS agencies At home care providers | Com Dev | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.10.10 Utilise City communications channels to proactively promote a message of preparedness relating to emergency services. | Yes | Planning & delivery Knowledge building | Community members are prepared for emergencies | # of messages | Ongoing | Officer time | DFES | Comms Emergency Services | Material Action Information | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury |
|  | 3.10.11 Develop Emergency Waste Management Plan | No | Planning & delivery | City is prepared to respond to waste following an emergency | Plan complete | 2027/28 | Officer time | DWER DFES | Emergency Services Waste | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental Safety & Quality |
|  | 3.10.12 Integrate natural hazard risk identification and mitigation into strategic planning, structure planning and development assessment to support safe and resilient communities. | No | Planning & delivery | Reduced exposure of people and property to natural hazards through informed land use planning and development outcomes. Enhanced community safety and resilience through planning processes and decisions that support outcomes which avoid or mitigate natural hazard risks. | Consideration of natural hazard risks in structure planning, subdivision and development assessment processes. Incorporation of hazard risk information and mitigation measures in approved planning and development proposals. | Ongoing | Grant funding Officer time Budget allocation | State agencies (DFES, DPLH, DoT, Water Corp) Landowners Developers State and Federal funding agencies | Planning Emergency Services Major Projects Engineering - City infrastructure Assets Development Engineering Sustainability Reserves | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental Safety Quality |
| 3.1 Facilitate initiatives that will support community members experiencing homelessness | 3.11.1 Advocate for funding for the Youth Foyer Project to support young people experiencing homelessness | No | Leadership & policy | Homeless young people are provided with safe accommodation and supported to transition to independence and a home. | Funding secured for the building and delivery of Youth Foyer project | Ongoing | Officer time | AYSA Advance Housing Albany Community Foundation | Mayor/Office of CEO Com Dev | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury Mental Health Equitable access |
|  | 3.11.2 Continue to provide free showering facilities, free Wi-Fi and access to PC's | Yes | Planning & delivery | Homeless and vulnerable people are supported through provision of showers and communication tools. | Continuation of services | Ongoing | Budget allocation |  | Library | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury Mental health Equitable access |
|  | 3.11.3 Support the delivery of the Housing First Initiative in Albany | No | Leadership & policy | Reduction in chronic or repeated homelessness Higher tenancy sustainment | Successful establishment of Housing First in Albany | Ongoing | Officer time | Office of Homelessness WAAEH Advance Housing AYSA ACF SAC Wagyl Kaip Pivot | Com Dev Manager Arts & Culture | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury Mental health Equitable access |
|  | 3.11.4 Encourage staff and community to support the Big Sleepout to raise funds for those experiencing homelessness | No | Leadership & policy | Increase in awareness of the causes of homelessness Increase in funding raised to support those experiencing homelessness | Staff participation | August each year | Officer time | ACF | People & Culture Com Dev Comms | Material Action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Mental health Equitable access |
|  | 3.11.5 Support and promote initiatives that raise awareness of homelessness in the community | Yes | Knowledge building | Increase in awareness of the causes of homelessness and support agencies | Delivery of homelessness initiatives | Ongoing | Officer time | WAAEH Office of Homelessness Anglicare Advance Housing Pivot Support Services AYSA ACF SAC | Com Dev Manager Arts & Culture Comms | Information | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Mental health Equitable access |
|  | 3.11.6 Support and link community members to local emergency and relief accommodation services | Yes | Knowledge building | Community members experiencing homelessness are linked with local emergency relief agencies | Community members linked with agencies | Ongoing | Officer time |  | Com Dev Rangers Library | Information | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Mental health Equitable access |
|  | 3.11.7 Partner with local agencies to facilitate to activities during Homelessness Week | No | Planning & delivery Knowledge building | Increase in awareness of the causes of homelessness and support agencies | Delivery of activities during Homelessness Week | August each year | Officer time Budget allocation Grant opportunities | ACF SAC Anglicare Pivot | Com Dev | Material action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury Mental health Equitable access |
| 3.12 Facilitate initiatives that will improve road and pedestrian safety | 3.12.1 Design and maintain local roads, including management and review of speed limits, to reduce the risk of crashes occurring and respond to changing land use and traffic | Yes | Planning & delivery | Albany’s road network is continually reviewed to increase safety of road users and pedestrians | Number of roads redesigned Number of speed limits reviewed | Ongoing | Officer time Budget allocation Grant opportunities |  | Assets Engineering | Material action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.12.2 Investigate feasibility of pedestrian counting via existing CCTV network and identify potential areas to enable counting and identify pedestrian crossing hotspots | No | Planning & delivery | Increase in data around where pedestrians are active and assist in signal warrant assessments | Software being investigated and CCTV mapped out with locations to be identified for counting. Trial counting if software is accepted. Additional cameras will be required per location. | 2026/27 | Officer time Budget allocation Grant opportunities |  | Assets Sustainability Information Technology | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.12.Identify projects that are eligible for Blackspot funding. | Yes | Planning & delivery | Improve known crash hotspots with federal funding if successful. | 1 application identified each year and documented | Ongoing | Officer time | MRWA | Engineering | Material Action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.12.4 Respond to reported hazards and dangers (road & footpath maintenance, roaming livestock, dog attacks, shark warnings etc) in a timely manner | Yes | Planning & delivery | Hazards are responded to quickly after being reported. | # of CSR closed | Ongoing | Officer time Budget allocation |  | Rangers Operations | Material action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.12.5 Participation and promotion of National Road Safety Partnership Program and National Road Safety Week Pledge | No | Leadership & Policy | Community awareness and participation. | # of social media posts Community participation | Ongoing | Officer time | Road Safety | Comms | Material action | Promote Equity & Inclusion Aboriginal Health & Wellbeing | Injury |
| 3.13 Support initiatives that aid in the prevention of violence (including family and domestic violence) | 3.13.1 Encourage community and staff to support 16 days of Activism Events | Yes | Leadership & policy | Great awareness of FDV amongst staff and community | # of events promoted | November each year | Officer time | Anglicare SAC | Com Dev People & culture | Material action & information | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
|  | 3.13.2 Continue to maintain the Public space CCTV network and expand as required in consultation with Police. | yes | Planning & delivery | Hot spot locations for crimes against the person are covered by CCTV to support Police response and for evidentiary purposes | # of cameras maintained # of new cameras | Ongoing | Officer time Annual budget | WAPOL City contractor DBCA | IT Com Dev | Material action | Prevent Aboriginal health & wellbeing Equity & inclusion | Injury |
| 3.14 Facilitate climate change adaptation to reduce its impact on health | 3.14.1 Develop plans to identify and support vulnerable community members during extreme heat/cold events and climate-related emergencies | No | Planning & delivery | Plans are in place for the City to support vulnerable community members during emergencies and extreme heat/cold events | Completion of plans | Q2, 2026/27 | Officer time | DFES WACHS | Community Services Emergency Services | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety & quality |
|  | 3.14.2 Undertake a shade audit for playgrounds and develop plan to increase shade | No | Planning & delivery | City has a plan to ensure that playgrounds have sufficient shade | Number of playgrounds with % shade | Funding dependent | Officer time Budget allocation Grant opportunities |  | Reserves | Material Action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety & quality |
|  | 3.14.3 Support initiatives that can increase community resilience to drought and disaster | No | Planning & Delivery | Residents have greater resilience and preparedness for drought and emergencies | # of initiatives delivered | Funding dependent | Officer time Grant opportunities | GSDC FRRR ADR | Com Dev | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Injury Environmental safety & quality Mental health |
|  | 3.14.4 Complete assessment (such as Climate Risk and Opportunity Management Program (CROMP) to identify, assess, manage, and disclose climate-related risks and opportunities, and support business continuity planning. | No | Planning & Delivery | The City is aware of and prepared for future risks. | Completed CROMP assessment | Q4 26-27 | Officer Time Budget allocation |  | Corporate Services Sustainability Emergency Services All | Material action | Protect Aboriginal health & wellbeing Equity & inclusion | Environmental Safety & Quality |
|  | 3.14.5 Develop information campaigns on the health impacts of climate change and how to prepare. | No | Planning & Delivery Leadership & Policy | Communications plan is develop and promoted in the lead up to extreme weather events | Development of a communications plan | 2027-28 | Officer time | DFES WACHS | Sustainability Comms Com Dev Emergency Services | Material action | Promote | Environmental Safety & Quality Diet Mental Health Equitable Access |
|  | 3.14.6 Support local, sustainable food systems to ensure food availability and affordability during extreme weather events and other crisis’s | No | Planning & Delivery Leadership & Policy | A risk assessment is undertaken to identify key challenges to Albany’s food system | Completion of the risk and impact assessment | 2027-28 | Officer time | Foodbank Elected members St Vincent de Paul WAPHA Anglicare Welfare network | Economic development Com Dev Corporate Services Emergency Services | Material action | Protect | Environmental Safety & Quality Diet Mental Health Equitable Access |